____________________________________________________________

INTEGRAL DRAGON

Applied Practice Alignment Update

Leadership alignment update · Ensemble Health Partners

____________________________________________________________

Prepared by Integral Dragon

Leadership alignment update · Ensemble Health Partners

Foundations complete. Applied Practice expanded from one week to four — and the first of those four is now in hand.

Justin Schmidt · Integral Dragon · 24 April 2026

____________________________________________________________

Where we are now

Phase 1 — Foundations — is complete.

Phase 2 — Applied Practice — began as a single week (Week 3 of the ten-week program). We expanded that one week into four so participants can do the work deliberately instead of sprint through it.

The four weeks of the expanded Applied Practice: Baseline (done) → Inspect & improve (next) → Validate → Adopt & review.

Week 1 is complete. Participants established a project-health baseline and identified the highest-friction risks in their codebase.

Three weeks remain inside Applied Practice — focused on improvement, validation, and team adoption.

Status chips:

Phase 1 · Foundations complete

Phase 2 · Week 1 of 4 complete

____________________________________________________________

What this phase is doing — and why we expanded it

Applied Practice shifts the emphasis from tool familiarity to improving project health in real codebases.

The original one-week compression did not give participants room to inspect, improve, validate, and review deliberately.

Four weeks gives each of those moves its own week, with evidence and a concrete output at the end of each.

The four weeks:

| Week | Focus | What participants produce |
| --- | --- | --- |
| 1 | Inspect | Project-health baseline + highest-friction areas |
| 2 | Improve | One bounded, AI-assisted candidate change on a branch |
| 3 | Validate | Tests, observability, and security review of the candidate change |
| 4 | Review & adopt | Comparison, adoption decision, and repeatable team practice |

What the expansion buys us:

Room to do the work, not just hear it explained.

Evidence collected and reviewed each week, not rolled up at the end.

Structural improvement we can measure — not self-reported "felt better."

The goal this serves:

Systems that are easier to understand.

Systems that are safer to change.

Systems that are easier to govern.

____________________________________________________________

Sample signals from the analysis

Both sides of the picture. Quantitative signals answer "how much, how often." Qualitative signals answer "what's the pattern." Each signal is sourced to a specific query or evidence pass — nothing floats.

Qualitative signals

Architecture clarity — can the team quickly explain system boundaries?

Documentation drift — are critical rules written down, or tribal knowledge?

Risk hotspots — where does change repeatedly cost more than estimated?

Testing confidence — do tests protect risky behavior, or chase coverage?

Workflow discipline — are changes reviewable, and actually reviewed?

Highest-leverage next move — one bounded improvement worth doing first.

Quantitative signals

File churn — top files by commit frequency, window over window.

Co-change pairs — which files keep moving together.

Cycle time — median hours from change opened to merged.

Review depth — reviewers, comment threads, PR-size distribution.

Release signals — CI pass rate, rollbacks, merge-to-prod latency.

Coverage snapshots — observability on hot paths, lockdown-test presence.

How we treat any one signal

Every signal is run across two consecutive windows. A signal that recurs across both is treated as structural. A signal that appears in only one window is flagged as tentative. That's what lets us tell leadership "this is real" versus "this was a bad week."